## Sheet1
Timeline
Tasks |  | 2018 | [10 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | J
Set up steering committee | bar: J
Phase 1: Project set-up
Contracts signing, fund establishment | bar: 2018 F to 2018 A
Hire project manager | bar: 2018 F
Hire project officer/s | bar: 2018 A to 2018 J
Set policies and protocols for the project | bar: 2018 J to 2018 J
Source a Chair for the GDG | bar: 2018 A to 2018 J
Source members for the GDG | bar: 2018 J to 2018 S
Source methodologist | bar: 2018 J to 2018 S
Source technical writers | bar: 2018 A to 2018 O
Formally establish the GDG | bar: 2018 O
Phase 2: Guideline development
GDG meeting 1 (introduction to guideline development, refining scope, setting questions & prioritising outcomes) | bar: 2018 N
Release Request for Quote if procuring systematic reviewer | bar: 2018 N
Write evidence review protocol | bar: 2018 D
Confirm protocol with GDG | bar: 2018 D
Consult on protocol if required | bar: 2018 D
Commence evidence review* | bar: 2019 J to 2019 M
GDG meeting 2 (review evidence and draft evidence statements) | bar: 2019 J
Draft evidence statements | bar: 2019 J
Finalise evidence review | bar: 2019 J
Develop draft of guideline | bar: 2019 J to 2019 J
GDG meeting 3 (draft recommendations) | bar: 2019 A
Draft supporting text | bar: 2019 S to 2019 O
Prepare Technical Report | bar: 2019 O
Prepare administrative report | bar: 2019 N
Start preparing for public consultation | bar: 2019 N
GDG meeting 4 (ratify draft guideline prior to public consultation) | bar: 2019 N
Phase 3: Public consultation
Produce communications strategy for public consultation | bar: 2019 N
Publish notice of public consultation | bar: 2019 D
Public consultation | bar: 2019 D to 2020 J
Collate submissions following close of public consultation | bar: 2020 F
Public consultation submission summary | bar: 2020 F
GDG meeting 5 (review public consultation submissions) | bar: 2020 M
Amend guideline | bar: 2020 A to 2020 M
Prepare public consultation summary report | bar: 2020 M
Prepare dissemination plan | bar: 2020 J
Prepare implementation strategy if required | bar: 2020 J
Phase 4: Finalisation and review
GDG meeting 6 (finalise draft CPG and imp plan) | bar: 2020 J
Make final amendments for draft guideline | bar: 2020 J to 2020 A
Conduct AGREE II assessments | bar: 2020 A
Conduct a methodological review | bar: 2020 A to 2020 S
Conduct independent review | bar: 2020 A to 2020 S
Finalise guideline | bar: 2020 S
GDG meeting 7 (ratify guideline, dissemination and implementation strategy and updating policy) | bar: 2020 O
Circulate for endorsement if required | bar: 2020 O
Phase 5: Publishing and dissemination
Publish guideline | bar: 2020 N
Prepare dissemination materials | bar: 2020 J to 2020 N
Conduct dissemination activities | bar: 2020 N to 2021 M
Publish guideline summaries and associated materials | bar: 2020 N to 2020 D
Phase 6: Evaluation and updating
Monitor triggers for updating | bar: 2020 D to 2021 J
Comply with updating policy | bar: 2020 D to 2021 J
*Search date must be within 12 months of public consultation release date
Legend
Tasks for the project team | bar: 2018 F
GDG meetings | bar: 2018 F
Milestone | bar: 2018 F